## Risk&Mitigation
Category | Risk | Description | Mitigation Strategy
Test Execution Risks | Incomplete Test Coverage | Some scenarios may not be covered due to lack of time or unclear requirements. | Prioritize high-risk areas, create a well-defined test strategy, and perform exploratory testing.
| Regression Testing Delays | Manual regression testing is time-consuming and may delay releases. | Automate repetitive test cases where possible and maintain a regression test suite.
Defect Management Risks | Duplicate Defects | Testers may report duplicate defects, wasting time and resources. | Maintain a well-organized defect tracking system and encourage team communication.
| Inconsistent Defect Reporting | Variations in defect descriptions may lead to misunderstandings. | Use a standard defect reporting template with clear steps and expected vs. actual results.
Test Planning & Execution Risks | Changing Requirements | Frequent requirement changes may impact test cases. | Maintain an agile test approach, continuously update test cases, and conduct impact analysis.
| Test Environment Issues | Inconsistent or unstable test environments can cause false failures. | Set up a dedicated test environment, perform environment checks before execution, and document dependencies.
Usability & Performance Testing Risks | Performance Bottlenecks | Manual testing cannot efficiently simulate high-load scenarios. | Use performance testing tools for load and stress testing in addition to manual observations.